## Legend
Challenger Picture Car Budget vs Breakdown - built 10/21/2026
Dates from Yellow one-liner 10/19; vehicles from breakdown 10/19 Latest (66 scenes, Days 19-29 + two Day 36). Original sheets/formulas untouched; 3 columns added at far right of car sheets.
Green = MATCHED to breakdown vehicle ask
Light yellow = POSSIBLE MATCH (unsure - check)
Orange = budget car NOT IN BREAKDOWN (scene/date shown if the budget names one)
Red = breakdown vehicle ask NOT IN BUDGET (sheet "Not in Budget" + bottom of Car Budget Daily)
Counts: matched 25, possible 14, budget-not-in-breakdown 48, breakdown-not-in-budget 18
AMBIGUITIES:
- Day 22 (Wed 10/21, Apollo) NASA VEHICLE count differs by scene: (5) in 101/18, 108/42, 101/5pt3, 101/5pt2 vs (7) in 101/7. 8 Savannah NASA vehicles budgeted - max needed unconfirmed.
- ND groups without counts: ND CARS (102/20, 102/52, 102/51, 104/9), ND NEIGHBORHOOD CARS (103/13pt1), ND CARS (RADIO/PRINT JOURNALISTS), NASA VEHICLE (104/21pt1), ND 80'S CAR (102/16).
- Same-named ND 80'S CAR groups on different days not confirmed to be the same cars.
- Most budget scenes (102-6, 102-21, 102-47, 103-7/23/26/40/46, 104-8/17/18/30/37/45 etc.) fall outside the Yellow 10/19 window, so they read NOT IN BREAKDOWN; that means "not in this breakdown", not cut.

## PicCarBudget
The Challenger-Block 1 | Picture Car Budget
Car Budget Totals
Amort Totals Block 1
Astro Van ROS
Labor Costs
Additional Labor
Equipment Costs
Modifications
Savannah Nasa Work
Picture Car Department Total

## Car Budget Daily
The Challenger | [7 empty] | Legend: | Green = matched | Yellow = possible | Orange = NOT IN BREAKDOWN
Block 2 | [8 empty] | Red rows at bottom = NOT IN BUDGET; see Legend sheet
Car Count
Car | ROS Rental | Daily Rental | Modifications/Repairs | Graphics/Paint | Days |  | Total | Usage Date(s) (Yellow 10/19) | Scene(s) (Breakdown) | Flag
Hoot's Van Double | 2750 |  | 1000 | 4000 | [5 empty] | NOT IN BREAKDOWN
Limo 102-6 |  | 800 |  | 4000 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
McNair Car #1 102-6 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
McNair Car #2 102-6 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
Police Car 102-6 |  | 550 |  | 800 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
News Van #1 102-6 | ROS Rental |  |  | 850 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
News Van #2 102-6 |  | 575 |  | 850 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
Journalist Suburbans x2 102-6 |  | 550 |  |  | 2 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
George TX Car |  | 695 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/14pt1 103/13pt2, 14pt2 103/13pt1 | POSSIBLE MATCH - POSSIBLE: "George TX Car" = GEORGE HOUSTON CAR? (also George Abbey Car 103-13 row)
Fiero x2 | ROS Rental | [6 empty] | Thu 10/22 D23 Gemini Tue 10/27 D26 | 102/16 101/73pt1 | MATCHED - Sally's Fiero (A) - 2 Fieros budgeted, breakdown lists (A) only
ND Cars 102-6 |  | 550 |  |  | 5 |  |  | (scene not in Yellow 10/19 window - no date) | 102/6 | NOT IN BREAKDOWN
Fiero x2 | ROS Rental | [6 empty] | Thu 10/22 D23 Gemini Tue 10/27 D26 | 102/16 101/73pt1 | MATCHED - Sally's Fiero (A) - 2 Fieros budgeted, breakdown lists (A) only
Steve's Car 102-16 |  | 550 |  |  | 1 |  |  | Thu 10/22 D23 Gemini | 102/16 | MATCHED
Hoot's Car 102-20 |  | 950 |  |  | 1 |  |  | Fri 10/16 D19 | 102/20 | NOT IN BREAKDOWN - Scene 102/20 is in breakdown (Day 19) but HOOT'S CAR is not listed there
Bill's Car 102-20 |  | 525 |  |  | 1 |  |  | Fri 10/16 D19 | 102/20 | MATCHED
ND Cars 102-20 |  | 550 |  |  | 3 |  |  | Fri 10/16 D19 | 102/20 | MATCHED - Breakdown ND CARS has no count (budget 3)
DC Town Car 102-21 |  | 675 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
News Van #1 102-21 | ROS Rental |  |  | 850 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
News Van #2 102-21 |  | 575 |  | 850 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
Second Pull up car 102-21 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
Journalist Suburbans x2 102-21 |  | 550 |  |  | 2 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
DC Patrol Car 102-21 |  | 500 |  | 750 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
ND Cars 102-21 |  | 550 |  |  | 6 |  |  | (scene not in Yellow 10/19 window - no date) | 102/21 | NOT IN BREAKDOWN
School Bus 102-47 |  | 775 |  | 4000 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 102/47 | NOT IN BREAKDOWN
ND Cars 102-47 |  | 550 |  |  | 6 |  |  | (scene not in Yellow 10/19 window - no date) | 102/47 | NOT IN BREAKDOWN
Pilot Mustang 102-51 |  | 695 |  |  | 1 |  |  | Thu 10/29 D28 | 102/51 | MATCHED
VW Beetle 102-51 |  | 1700 |  |  | 1 |  |  | Thu 10/29 D28 | 102/51 | MATCHED
Hoot's Car 102-51 |  | 950 |  |  | 1 |  |  | Thu 10/29 D28 | 102/51 | NOT IN BREAKDOWN - Scene 102/51 is in breakdown (Day 28) but HOOT'S CAR is not listed there
Broken Taillight Sedan 102-51 |  | 500 |  |  | 1 |  |  | Thu 10/29 D28 | 102/51 | MATCHED
ND Cars 102-51 |  | 550 |  |  | 15 |  |  | Thu 10/29 D28 | 102/51 | MATCHED - Breakdown ND CARS has no count (budget 15)
Onizuka SUV 103-3 |  | 550 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - ONIZUKA CARS (2)
El Onizuka Car 103-3 |  | 550 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - ONIZUKA CARS (2)
News Van #1 103-3 | ROS Rental |  |  | 850 | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - NEWS VANS (3)
News Van #2 103-3 |  | 575 |  | 850 | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - NEWS VANS (3)
News Van #3 103-3 |  | 575 |  | 850 | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - NEWS VANS (3)
Journalist Suburbans x2 103-3 |  | 550 |  |  | 2 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | POSSIBLE MATCH - POSSIBLE: = ND CARS (RADIO/PRINT JOURNALISTS)? no count in breakdown
Nasa Van 103-3 | ROS Rental |  |  | 500 | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED
ND Cars 103-3 |  | 550 |  |  | 5 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | MATCHED - Count differs: budget 5 vs breakdown ND 80'S CAR (4)
Commision Van #2 103-7 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 103/7 | NOT IN BREAKDOWN
Hoots Car 103-13 |  | 950 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/14pt1 103/13pt2, 14pt2 103/13pt1 | MATCHED
Joyce Abbey Wagon 103-13 |  | 695 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/14pt1 103/13pt2, 14pt2 | MATCHED - = JOYCE ABBEY HOUSTON CAR
George Abbey Car 103-13 |  | 695 |  |  | 1 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/14pt1 103/13pt2, 14pt2 103/13pt1 | MATCHED - = GEORGE HOUSTON CAR
ND Cars (1978) 103-13 |  | 550 |  |  | 5 |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/14pt1 103/13pt2, 14pt2 103/13pt1 | MATCHED - = ND NEIGHBORHOOD CARS (5); 13pt1 has no count
ND Cars 103-23 |  | 550 |  |  | 20 |  |  | (scene not in Yellow 10/19 window - no date) | 103/23 | NOT IN BREAKDOWN
ND Cars 103-26 |  | 550 |  |  | 6 |  |  | (scene not in Yellow 10/19 window - no date) | 103/26 | NOT IN BREAKDOWN
Astrovan Escort Car 103-40 |  | 500 |  | 650 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 103/40 | NOT IN BREAKDOWN
Hoot's Van 103-46 |  | 500 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 103/46 | NOT IN BREAKDOWN
Hoot's Van Double 103-46 | ROS Rental |  |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 103/46 | NOT IN BREAKDOWN
ND Cars 103-46 |  | 550 |  |  | 5 |  |  | (scene not in Yellow 10/19 window - no date) | 103/46 | NOT IN BREAKDOWN
McNair Car (1982) 104-8 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/8 | NOT IN BREAKDOWN
McNair Incident Truck #1 |  | 500 |  |  | 1 |  |  |  |  | NOT IN BREAKDOWN
McNair Incident Truck #2 |  | 500 |  |  | 1 |  |  |  |  | NOT IN BREAKDOWN
El's Car 104-9 |  | 550 |  |  | 1 |  |  | Thu 10/29 D28 | 104/9 | MATCHED
Arnie Thompson Truck 104-17 |  | 650 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/17 | NOT IN BREAKDOWN
ND Cars x10 104-17 |  | 550 |  |  | 10 |  |  | (scene not in Yellow 10/19 window - no date) | 104/17 | NOT IN BREAKDOWN
Joyce Abbey Wagon 104-18 |  | 695 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/18 | NOT IN BREAKDOWN
McNair Car #1 104-18 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/18 | NOT IN BREAKDOWN
McNair Car #2 104-18 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/18 | NOT IN BREAKDOWN
Boisjoly Car 104-22 |  | 525 |  |  | 1 |  |  | Fri 10/23 D24 | 108/1 | POSSIBLE MATCH - POSSIBLE: budget says 104-22, breakdown has BOISJOLY CAR at 108/1 (104/22 not in Yellow window)
Joyce Abbey Wagon 104-30 |  | 695 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/30 | NOT IN BREAKDOWN
McNair Car 104-30 |  | 550 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/30 | NOT IN BREAKDOWN
Other Family Cars x2 104-30 |  | 550 |  | 0 | 2 |  |  | (scene not in Yellow 10/19 window - no date) | 104/30 | NOT IN BREAKDOWN
ND Cars 104-30 |  | 550 |  |  | 4 |  |  | (scene not in Yellow 10/19 window - no date) | 104/30 | NOT IN BREAKDOWN
Second NASA Van 104-37 |  | 550 |  | 450 | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/37 | NOT IN BREAKDOWN
ND Cars 104-37 |  | 550 |  |  | 6 |  |  | (scene not in Yellow 10/19 window - no date) | 104/37 | NOT IN BREAKDOWN
Hoot's Van 104-45 |  | 500 |  |  | 1 |  |  | (scene not in Yellow 10/19 window - no date) | 104/45 | NOT IN BREAKDOWN
Hoot's Van Double 104-45 | ROS Rental | [6 empty] | (scene not in Yellow 10/19 window - no date) | 104/45 | NOT IN BREAKDOWN
ND x10 104-45 |  | 550 |  |  | 10 |  |  | (scene not in Yellow 10/19 window - no date) | 104/45 | NOT IN BREAKDOWN
ND x3 104-21 |  | 500 |  |  | 3 |  |  | Thu 10/22 D23 Gemini | 104/21pt1 | POSSIBLE MATCH - POSSIBLE: 104/21pt1 lists only "NASA VEHICLE" (no count); budget ND x3
Ice Team Van 104-21 | ROS Rental | [6 empty] | Thu 10/22 D23 Gemini | 104/21pt1 | POSSIBLE MATCH - POSSIBLE: 104/21pt1 "KSC - VAN" lists NASA VEHICLE, no Ice Team Van by name
Before Tax
Sales Tax
Savannah Work Tab
Modifications, Builds, stunt prep
Misc Parts, Materials, Tires, Supplies, Tint replacement Spend | [6 empty] | 10500
BREAKDOWN VEHICLE ASKS NOT IN BUDGET (18) - see "Not in Budget" sheet
Vehicle ask (breakdown, verbatim) | Count | Scene | Date | Day # | Unit | Set | Note
ND CARS | (no count) | 102/52 | Fri 10/16/2026 | 19 | Main | EXT SALLY'S APARTMENT COMPLEX - STAIRS/PARKING LOT/ JUDY'S APT
ND 80'S CAR (4) | 4 | 108/24 | Mon 10/19/2026 | 20 | Apollo | EXT KSC - COMPLEX C - TRAILER
HOOT'S FLORIDA RENTAL VAN | (no count) | 104/42 | Tue 10/20/2026 | 21 | Main | EXT DIVE BAR - FL | Possibly Hoot's Van / Van Double (budgeted only for 103-46, 104-45)
ND 80'S CAR (5) | 5 | 104/42 | Tue 10/20/2026 | 21 | Main | EXT DIVE BAR - FL
ND 80'S CAR | (no count) | 102/16 | Thu 10/22/2026 | 23 | Gemini | EXT SALLY/STEVE’S HOME - GARAGE/DRIVEWAY
AL'S CAR | (no count) | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
ND 80'S CAR (10) | 10 | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
VEHICLE FROM BG (3) | 3 | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
ND CARS (15) | 15 | 108/31A, 32A | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - ENTRANCE
JUDY'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
RHEA'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
SALLY'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
VEHICLE FROM BG (5) | 5 | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
STORE PATRON'S CAR (2) | 2 | 101/73pt1 | Tue 10/27/2026 | 26 | Main | EXT CONVENIENCE STORE - PARKING LOT
VEHICLE FROM BG (2) | 2 | 101/73pt1 | Tue 10/27/2026 | 26 | Main | EXT CONVENIENCE STORE - PARKING LOT
HOOT'S CAR | (no count) | 104/9 | Thu 10/29/2026 | 28 | Main | EXT PARKING LOT - OUTPOST - HOUSTON | Hoot's Car budgeted for 102-20/102-51/103-13 but not 104-9
ND CARS | (no count) | 104/9 | Thu 10/29/2026 | 28 | Main | EXT PARKING LOT - OUTPOST - HOUSTON
ND 80'S CAR (2) | 2 | 108/15 | Fri 10/30/2026 | 29 | Main | INT JUDY'S HOUSE - SUNROOM/LIVING ROOM

## AmortVechicles
| ROS Rental | Per Day Price | Repairs/Refurbish | Graphics/Paint | On set Modifications | Days | Total | Amort | Usage Date(s) (Yellow 10/19) | Scene(s) (Breakdown) | Flag
Pontiac Fiero #1 | 6000 |  | 1500 |  | 1700 |  |  |  | Thu 10/22 D23 Gemini Tue 10/27 D26 | 102/16 101/73pt1 | MATCHED
Pontiac Fiero #2 | 9000 |  | 1500 | [5 empty] | Thu 10/22 D23 Gemini Tue 10/27 D26 | 102/16 101/73pt1 | MATCHED
Opel GT | 6000 |  |  | 3500 | [6 empty] | NOT IN BREAKDOWN
Itasca Motorhome STS7 STS8 | 6500 |  | 5000 | [7 empty] | NOT IN BREAKDOWN
Ice Team Van NASA | 4500 |  |  | 3000 |  |  |  |  | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/7 101/5pt3 101/5pt2 | MATCHED
News Van | 6500 |  |  | 1500 |  |  |  |  | Mon 10/19 D20 Gemini Mon 10/19 D20 Gemini | 103/3 103/4 | POSSIBLE MATCH - POSSIBLE: amortized News Van may be one of NEWS VANS (3) 103/3-4
Sales Tax
Block Total

## Astro Van
| ROS | Graphics | Paint | Totals | Amort | Usage Date(s) (Yellow 10/19) | Scene(s) (Breakdown) | Flag
AstroVan Airstream** | 16500 | 2000 | 2000 |  |  | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 | MATCHED
Sales Tax
Total

## PicCarLabor
Picture Car Coordinator | Rate | Avg Hours | Tool Kit | Truck Rental | Meal $ | Phone | Laptop | Per Day
Chad Kinsey | 56.5 | 12 | 25 | 80 | 50 | 3 | 10
| 56.5 | 12 | 25 | 80 | 50 | 3 | 10
| 56.5 | 10 | 25 | 80 | 0 | 3 | 10
| Days @ 10 | 0
| Days @ 12 | 26
| Days @ 13 | 0 | [6 empty] | Total
| 6th Day Load ins | 0
| Holiday | 0
Picture Car Captain
Greg Smith | 54.82 | 12 | 25 | 80 | 50 | 3
| 54.82 | 10 | 25 | 80 | 0 | 3
| Days @ 10 | 0
| Days @ 12 | 26 | [6 empty] | Total
| Holiday | 0
| 6th Day Load Ins | 0
Picture Car Mechanic
Ricky Sosebee | 52.8 | 12 | 40 | 80 | 50 | 3
| 52.8 | 10 | 40 | 80 | 0 | 3
| Days @ 10 | 0
| Days @ 12 | 26 | [6 empty] | Total
| Holiday | 0
Picture Car Driver
Benny Loudermilk | 52.31 | 12 | 0 | 0 | 50 | 3 | 0
| 52.31 | 10 | 0 | 0 | 0 | 3 | 0
| Days @ 10 | 0 | [6 empty] | Total
| Days @ 12 | 26
| Holiday | 0
| 6th Day Load Ins | 0
Total Labor

## AdditionalLabor
Picture Car Mechanic
Day Player as needed big days | 52.8 | 12 | 40 | 80 | 50 | 3
and tandem unit days | 52.8 | 10 | 40 | 80 | 0 | 3
| Days @ 10 | 0
| Days @ 12 | 3
| Holiday | 0
Picture Car Driver
LANDOLL DRIVER-Savannah Work | 52.31 | 12 | 0 | 0 | 50 | 3 | 0
| 52.31 | 10 | 0 | 0 | 0 | 3 | 0
| Days @ 10 | 0
| Days @ 12 | 7
| Holiday | 0
| 6th Day Load Ins | 0
Picture Car Driver
Car Hauler Splinter Unit Work | 52.31 | 12 | 0 | 0 | 50 | 3 | 0
| 52.31 | 10 | 0 | 0 | 0 | 3 | 0
| Days @ 10 | 0
| Days @ 12 | 7
| Holiday | 0
| 6th Day Load Ins | 0
Total

## PicCarEquipment
Hauler Truck and Trailer
Weekly | 1600
Weeks | 5.2
Shop $1000 per week | 5200
Single Car Tilt Trailer | 200
Days | 5
Savannah Move Landoll | 3250
weeks | 2
Additonal Truck | 250
Additional Trailer | 175
Total
Days | 7
Subtotal
Tax
Total

## Modifications Tab
Modifications
STS7 Interior Build |  | 0 | Not Block 1
STS7 Repaint for EFB |  | 0 | Not Block 1
Fiero Rear Glass |  | 0
Fiero Rear Glass R&R Glazer | 100.00 per hour | 0 | Canceled?
Tax |  | 0
0

## Savannah Work
Nasa Vehicle #1 Gray Step Van Savannah | 700 |  |  | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #2 Dodge Van Savannah | 500 |  |  | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #3 Gray Isuzu Savannah | 650 |  |  | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #4 Chevy Van Savannah | 500 |  |  | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #5 Gray Step Van #2 Savannah | 700 |  |  | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #6 Gray Flat Bed Savannah | 500 |  | 500 | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #7 Dodge Truck Painted White Savannah | 550 |  | 3500 | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
Nasa Vehicle #8 K5 Blazer Savannah | 550 |  | 3500 | 1 | Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo Wed 10/21 D22 Apollo | 101/18 108/42 101/5pt3 101/5pt2 101/7 | POSSIBLE MATCH - POSSIBLE: Day 22 NASA VEHICLE (5) / (7) - 8 Savannah NASA vehicles budgeted; max needed unconfirmed
News Van #1 Savannah | 775 |  | 1000 | 1 |  |  | NOT IN BREAKDOWN
News Van #2 Savannah | 500 |  | 1000 | 1 |  |  | NOT IN BREAKDOWN
[5 empty] | ^ Usage Date(s) (Yellow 10/19) (column header) | ^ Scene(s) (Breakdown) (column header) | ^ Flag (column header)
Sales Tax

## Not in Budget
Vehicle ask (breakdown, verbatim) | Count | Scene | Date | Day # | Unit | Set | Note
ND CARS | (no count) | 102/52 | Fri 10/16/2026 | 19 | Main | EXT SALLY'S APARTMENT COMPLEX - STAIRS/PARKING LOT/ JUDY'S APT
ND 80'S CAR (4) | 4 | 108/24 | Mon 10/19/2026 | 20 | Apollo | EXT KSC - COMPLEX C - TRAILER
HOOT'S FLORIDA RENTAL VAN | (no count) | 104/42 | Tue 10/20/2026 | 21 | Main | EXT DIVE BAR - FL | Possibly Hoot's Van / Van Double (budgeted only for 103-46, 104-45)
ND 80'S CAR (5) | 5 | 104/42 | Tue 10/20/2026 | 21 | Main | EXT DIVE BAR - FL
ND 80'S CAR | (no count) | 102/16 | Thu 10/22/2026 | 23 | Gemini | EXT SALLY/STEVE’S HOME - GARAGE/DRIVEWAY
AL'S CAR | (no count) | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
ND 80'S CAR (10) | 10 | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
VEHICLE FROM BG (3) | 3 | 108/1 | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - PARKING LOT
ND CARS (15) | 15 | 108/31A, 32A | Fri 10/23/2026 | 24 | Main | EXT MORTON THIOKOL - ENTRANCE
JUDY'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
RHEA'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
SALLY'S HOUSTON RENTAL CAR | (no count) | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
VEHICLE FROM BG (5) | 5 | 101/42 | Mon 10/26/2026 | 25 | Main | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR
STORE PATRON'S CAR (2) | 2 | 101/73pt1 | Tue 10/27/2026 | 26 | Main | EXT CONVENIENCE STORE - PARKING LOT
VEHICLE FROM BG (2) | 2 | 101/73pt1 | Tue 10/27/2026 | 26 | Main | EXT CONVENIENCE STORE - PARKING LOT
HOOT'S CAR | (no count) | 104/9 | Thu 10/29/2026 | 28 | Main | EXT PARKING LOT - OUTPOST - HOUSTON | Hoot's Car budgeted for 102-20/102-51/103-13 but not 104-9
ND CARS | (no count) | 104/9 | Thu 10/29/2026 | 28 | Main | EXT PARKING LOT - OUTPOST - HOUSTON
ND 80'S CAR (2) | 2 | 108/15 | Fri 10/30/2026 | 29 | Main | INT JUDY'S HOUSE - SUNROOM/LIVING ROOM