## DOOD
The Challenger - Picture Car DOOD from breakdown "Latest" (PDF dated 10/19/2026) - days/dates/units mapped from YELLOW 10/19 one-liner
Date | 2026-10-16 | 2026-10-19 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-21 | 2026-10-22 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-10
Day | Fri | Mon | Mon | Tue | Wed | Wed | Thu | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Tue
Shoot Day | 19 | 20 | 20 | 21 | 22 | 22 | 23 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 36
Unit | - | Apollo | Gemini | - | Apollo | Gemini | Apollo | Gemini | - | - | - | - | - | - | -
Set(s) | E/I APARTMENT COMPLEX - CLEAR LAKE INT SALLY'S APARTMENT - KITCHEN INT SALLY’S APARTMENT - APARTMENT COMPLEX EXT SALLY'S APARTMENT COMPLEX - STAIRS/PARKING LOT/ | INT MORTON THIOKOL - DRAFTING TABLE INT MORTON THIOKOL - BOISJOLY’S OFFICE INT MORTON THIOKOL - BULLPEN INT KSC - COMPLEX C - TRAILER EXT KSC - COMPLEX C - TRAILER | EXT ONIZUKA HOME - PATH/DRIVEWAY I/E ONIZUKA HOME - FRONT ROOM/ROAD I/E GEORGE/JOYCE'S HOUSE - LIVING ROOM EXT GEORGE’S HOUSE I/E HOOT'S CAR/GEORGE’S HOUSE | INT DIVE BAR - FL EXT DIVE BAR - FL | EXT KSC - LAUNCH PAD 39B EXT KSC - FSS - LAUNCHPAD 39B EXT KSC - LAUNCHPAD 39B INT KSC - VAN EXT KSC - VAN | INT MORTON THIOKOL - CONF. ROOM INT EMERGENCY WING - SOUTHEAST MEMORIAL HOSPITAL INT MSFC - CONF ROOM | INT MSFC - MULLOY’S OFFICE INT KSC - LCC - MEN'S BATHROOM INT MORTON THIOKOL - BULLPEN/CONF. ROOM INT MORTON THIOKOL - CONF. ROOM INT MORTON THIOKOL - BOISJOLY’S OFFICE | EXT KSC - VAN - TRAVELING THROUGH KSC / VISITOR CENTER INT VISITOR CENTER - KENNEDY - FL INT KSC - LAB EXT SALLY/STEVE’S HOME - GARAGE/DRIVEWAY | INT MORTON THIOKOL - CONF. ROOM INT MORTON THIOKOL - BULLPEN EXT MORTON THIOKOL - PARKING LOT EXT MORTON THIOKOL - ENTRANCE INT MORTON THIOKOL - BULLPEN/CONF. ROOM INT MORTON THIOKOL - BULLPEN/AL'S OFFICE | E/I JSC - GUARD BOOTH / SALLY'S RENTAL CAR INT OUTPOST | INT OUTPOST - HOUSTON EXT CONVENIENCE STORE - PARKING LOT | INT BATHROOM - OUTPOST INT OUTPOST - HOUSTON | INT OUTPOST - HOUSTON EXT OUTPOST - PARKING LOT EXT PARKING LOT - OUTPOST - HOUSTON | INT JUDY'S HOUSE - KITCHEN INT JUDY'S HOUSE - SUNROOM/LIVING ROOM INT JUDY'S HOUSE - SUNROOM/LIVING ROOM/KITCHEN INT HOLIDAY INN - SALLY'S ROOM | INT MORTON THIOKOL - CONF. ROOM INT MORTON THIOKOL - BULLPEN/BOISJOLY'S OFFICE
Scenes (ep/sc) | 102/20 103/9 102/53 102/54 102/JUDY'S APT | 108/7 101/66 108/34B 108/61, 62, 63 108/61, 62, 63 108/24 | 103/4 103/69 103/14pt1 103/13pt2, 14pt2 103/13pt1 | 104/40 104/41 104/41 CONT 104/517X, 518X, 521X | 101/500X, 810X, 811X, 812X 108/500X, 810X, 811X, 812X 101/801X 101/801X 101/801X | 102/28pt2 102/30pt2 103/37, 36pt1 104/15 103/2 | 108/4 101/70 108/23 108/25pt, 26, 108/31 | 104/21pt1 104/24 104/33 102/16 | 101/1 101/500X 108/1 108/31A, 32A 108/53 108/2 | 101/42 101/49 | 108/22, 24, 26, 27, 28, 29, 31, 41, 108/22, 24, 26, 27, 28, 29, 31, 41, 101/73pt1 | 106/22 106/21 102/42, 69 107/3 | 104/69, 163 104/29, 41, 42, 43, 69, 163 104/28, 29, 41, 42, 43, 69, 163 104/28, 29, 41, 42, 43, 69, 163 102/809X 104/9 | 107/48 108/15 102/2 104/47 | 103/31 104/23
Car Count | 2 | 4 | 20 | 6 | 14 | 0 | 0 | 4 | 30 | 8 | 5 | 0 | 6 | 2 | 0
Vehicle (as listed in breakdown)
BILL'S CAR | SWF 102/20
ND CARS | SW 102/20, 102/JUDY'S APT | H | H | H | H | H | H | H | H | H | H | H | WF 102/809X, 104/9
ND 80'S CAR (4) |  | SW 108/24 | WF 103/4, 103/69
NASA VAN |  |  | SWF 103/4, 103/69
ND CARS (RADIO/PRINT JOURNALISTS) |  |  | SWF 103/4, 103/69
NEWS VANS (3) |  |  | SWF 103/4, 103/69
ONIZUKA CARS (2) |  |  | SWF 103/4, 103/69
GEORGE HOUSTON CAR |  |  | SWF 103/14pt1, 103/13pt2, 14pt2, 103/13pt1
HOOT'S CAR |  |  | SW 103/14pt1, 103/13pt2, 14pt2, 103/13pt1 | H | H | H | H | H | H | H | H | H | WF 104/9
JOYCE ABBEY HOUSTON CAR |  |  | SWF 103/14pt1, 103/13pt2, 14pt2
ND NEIGHBORHOOD CARS (5) |  |  | SWF 103/14pt1, 103/13pt2, 14pt2
ND NEIGHBORHOOD CARS |  |  | SWF 103/13pt1
HOOT'S FLORIDA RENTAL VAN |  |  |  | SWF 104/517X, 518X, 521X
ND 80'S CAR (5) |  |  |  | SWF 104/517X, 518X, 521X
ASTROVAN |  |  |  |  | SWF 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X
ICE TEAM VAN #1 (WHITE VAN) |  |  |  |  | SWF 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X, 101/801X, 101/801X, 101/801X
NASA VEHICLE (5) |  |  |  |  | SWF 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X, 101/801X, 101/801X
NASA VEHICLE (7) |  |  |  |  | SWF 101/801X
NASA VEHICLE | [7 empty] | SWF 104/21pt1
ND 80'S CAR | [7 empty] | SWF 102/16
SALLY'S FIERO (A) | [7 empty] | SW 102/16 | H | H | WF 101/73pt1
STEVE'S CAR | [7 empty] | SWF 102/16
AL'S CAR | [8 empty] | SWF 108/1
BOISJOLY CAR | [8 empty] | SWF 108/1
ND 80'S CAR (10) | [8 empty] | SWF 108/1
VEHICLE FROM BG (3) | [8 empty] | SWF 108/1
ND CARS (15) | [8 empty] | SWF 108/31A, 32A
JUDY'S HOUSTON RENTAL CAR | [9 empty] | SWF 101/42
RHEA'S HOUSTON RENTAL CAR | [9 empty] | SWF 101/42
SALLY'S HOUSTON RENTAL CAR | [9 empty] | SWF 101/42
VEHICLE FROM BG (5) | [9 empty] | SWF 101/42
STORE PATRON'S CAR (2) | [10 empty] | SWF 101/73pt1
VEHICLE FROM BG (2) | [10 empty] | SWF 101/73pt1
BROKEN TAILLIGHT CAR | [12 empty] | SWF 102/809X
MUSTANG (PILOT) | [12 empty] | SWF 102/809X
VW BEETLE | [12 empty] | SWF 102/809X
EL'S CAR | [12 empty] | SWF 104/9
ND 80'S CAR (2) | [13 empty] | SWF 108/15
Notes
Source PDF is a scene breakdown report (no day breaks). Shoot day/date/unit per scene come from the Yellow 10/19 one-liner; all 67 breakdown scenes matched exactly one Yellow day.
Counts in "(n)" are as printed; un-numbered ND CARS / ND NEIGHBORHOOD CARS counted as 1 (AMBIGUOUS - quantity not given).
Codes: SW start, W work, H hold (idle between work days), WF finish, SWF single day. Same-named vehicle on multiple days treated as the same unit (ND groups may not be the same cars - Chad to confirm).
Days with no vehicles in the breakdown show 0. Day 36 (11/10) contains only Thiokol conf-room scenes 103/31 and 104/23.
Note on B11: Scenes: 102/20
Note on B12: Scenes: 102/20, 102/JUDY'S APT
Note on N12: Scenes: 102/809X, 104/9
Note on C13: Scenes: 108/24
Note on D13: Scenes: 103/4, 103/69
Note on D14: Scenes: 103/4, 103/69
Note on D15: Scenes: 103/4, 103/69
Note on D16: Scenes: 103/4, 103/69
Note on D17: Scenes: 103/4, 103/69
Note on D18: Scenes: 103/14pt1, 103/13pt2, 14pt2, 103/13pt1
Note on D19: Scenes: 103/14pt1, 103/13pt2, 14pt2, 103/13pt1
Note on N19: Scenes: 104/9
Note on D20: Scenes: 103/14pt1, 103/13pt2, 14pt2
Note on D21: Scenes: 103/14pt1, 103/13pt2, 14pt2
Note on D22: Scenes: 103/13pt1
Note on E23: Scenes: 104/517X, 518X, 521X
Note on E24: Scenes: 104/517X, 518X, 521X
Note on F25: Scenes: 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X
Note on F26: Scenes: 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X, 101/801X, 101/801X, 101/801X
Note on F27: Scenes: 101/500X, 810X, 811X, 812X, 108/500X, 810X, 811X, 812X, 101/801X, 101/801X
Note on F28: Scenes: 101/801X
Note on I29: Scenes: 104/21pt1
Note on I30: Scenes: 102/16
Note on I31: Scenes: 102/16
Note on L31: Scenes: 101/73pt1
Note on I32: Scenes: 102/16
Note on J33: Scenes: 108/1
Note on J34: Scenes: 108/1
Note on J35: Scenes: 108/1
Note on J36: Scenes: 108/1
Note on J37: Scenes: 108/31A, 32A
Note on K38: Scenes: 101/42
Note on K39: Scenes: 101/42
Note on K40: Scenes: 101/42
Note on K41: Scenes: 101/42
Note on L42: Scenes: 101/73pt1
Note on L43: Scenes: 101/73pt1
Note on N44: Scenes: 102/809X
Note on N45: Scenes: 102/809X
Note on N46: Scenes: 102/809X
Note on N47: Scenes: 104/9
Note on O48: Scenes: 108/15